## Forward Traceability
Requirements | Tests | Executions | Defects
PIM-31 - Personal Details in Add Employee functionality | PIM-34 - Verify that license expiry date accepts only format yyyy-mm-dd | Implementation of the PIM Module - PASS | None
PIM-31 - Personal Details in Add Employee functionality | PIM-35 - Verify that user should not able to edit the dropdown value of 'Marital Status' | Implementation of the PIM Module - PASS | None
PIM-11 - Immigration in Add Employee functionality | PIM-40 - Verify that only one radio button can be selected at a time | Implementation of the PIM Module - PASS | None
PIM-11 - Immigration in Add Employee functionality | PIM-41 - Verify that Expiry Date can not be an earlier date than Issued Date | Implementation of the PIM Module - PASS | None
PIM-10 - Dependents in Add Employee functionality | PIM-38 - Verify that user can not save action when no field was filled in | Implementation of the PIM Module - PASS | None
PIM-10 - Dependents in Add Employee functionality | PIM-39 - Verify that user can Copy and Paste texts from word or notepad into 'Name' field | Implementation of the PIM Module - PASS | None
PIM-9 - Emergency Contact in Add Employee functionality | PIM-36 - Verify that "Mobile" field does not accept letters | Implementation of the PIM Module - PASS | None
PIM-9 - Emergency Contact in Add Employee functionality | PIM-37 - Verify that user can cancel action when all the fields are completed | Implementation of the PIM Module - PASS | None
PIM-8 - Add Employee functionality - 1 defect | PIM-33 - Verify that other type of file is accepted as photograph | Implementation of the PIM Module - FAIL | PIM-47 - In Progress - Accepted as photograph another file extension than jpg, png, gif.
PIM-8 - Add Employee functionality | PIM-30 - Verify that an employee can be added | Implementation of the PIM Module - PASS | None
PIM-5 - Termination Reasons in Configuration functionality | PIM-28 - Verify that user can cancel action when the field is completed | Implementation of the PIM Module - PASS | None
PIM-5 - Termination Reasons in Configuration functionality | PIM-29 - Verify that a termination reason name can be edited | Implementation of the PIM Module - PASS | None
PIM-5 - Termination Reasons in Configuration functionality | PIM-44 - Verify that the asterisk is displayed next to "Name" mandatory field | Implementation of the PIM Module - PASS | None
PIM-4 - Reporting Methods in Configuration functionality | PIM-25 - Verify field "Name" how many characters accepts | Implementation of the PIM Module - PASS | None
PIM-4 - Reporting Methods in Configuration functionality | PIM-26 - Verify that "Name" field accepts upper and lower case both | Implementation of the PIM Module - PASS | None
PIM-4 - Reporting Methods in Configuration functionality | PIM-27 - Verify that multiple entries of reporting methods can be deleted at the same time | Implementation of the PIM Module - PASS | None
PIM-3 - Data Import in Configuration functionality | PIM-22 - Verify that “Sample CSV file” can be downloaded | Implementation of the PIM Module - PASS | None
PIM-3 - Data Import in Configuration functionality | PIM-23 - Verify if another type of file can be uploaded | Implementation of the PIM Module - PASS | None
PIM-3 - Data Import in Configuration functionality | PIM-24 - Verify that a correctly completed CSV file with size lesser than 1 MB can be uploaded | Implementation of the PIM Module - PASS | None
PIM-3 - Data Import in Configuration functionality | PIM-43 - Ensure that a hand icon is displayed when mouse pointer is hovered over the "Download" link | Implementation of the PIM Module - PASS | None
PIM-2 - Custom Fields in Configuration functionality | PIM-18 - Verify that "Field Name" accepts any type of characters | Implementation of the PIM Module - PASS | None
PIM-2 - Custom Fields in Configuration functionality - 1 defect | PIM-21 - Verify that "Select options" field accepts values separated by another characters than commas | Implementation of the PIM Module - FAIL | PIM-45 - In Progress - Values separated by another characters than commas
PIM-2 - Custom Fields in Configuration functionality | PIM-16 - Verify that a custom field can be added | Implementation of the PIM Module - PASS | None
PIM-2 - Custom Fields in Configuration functionality | PIM-17 - Check that “Field name” is mandatory field | Implementation of the PIM Module - PASS | None
PIM-2 - Custom Fields in Configuration functionality | PIM-20 - Verify that a custom field can be deleted | Implementation of the PIM Module - PASS | None
PIM-2 - Custom Fields in Configuration functionality | PIM-19 - Verify that user can cancel action when edit a custom field | Implementation of the PIM Module - PASS | None
PIM-2 - Custom Fields in Configuration functionality | PIM-42 - Verify that 'Delete’ button remains inactive until one of entry is selected | Implementation of the PIM Module - PASS | None
PIM-1 - Optional Fields in Configuration functionality - 1 defect | PIM-14 - Verify that all optional fields can be added | Implementation of the PIM Module - FAIL | PIM-46 - In Progress - Show US Tax Exemptions menu was not added
PIM-1 - Optional Fields in Configuration functionality | PIM-13 - Verify that an optional field can be added | Implementation of the PIM Module - PASS | None
PIM-1 - Optional Fields in Configuration functionality | PIM-15 - Verify that the checkbox can be deselected | Implementation of the PIM Module - PASS | None